## PRODUCT BACKLOG
PRODUCT BACKLOG EXAMPLE (Game of the Goose)
ID | Feature | Category | Priority | Sprint 1 | Sprint 2 | Sprint 3
0 | Display menu screen on program start | Menu | M
1 | Menu with "start game" and "exit" buttons | Menu | M
2 | Show the rules of the game when needed by user | Menu or Turn | M
3 | Screen to select the number of players | Init | M
4 | Display game board | Init | M
5 | Place all pawns on first tile | Init | M
6 | Display "exit" button | Init and Turn | M
7 | Display which player is playing the current turn | Turn | M
8 | Current player can roll the dice and see the result | Turn | M
9 | Move the pawn of the player forward according to dice result | Turn | M
10 | Execute special actions (for example, go back to tile 1) according to the tile on which the player arrives | Turn | M
11 | Change current player after the end of the turn | Turn | M
12 | Show win screen if current player arrives to end tile and display name of winner | End | M
13 | "Go back to menu" button is displayed in the win screen | End | S
14 | Current player can pause and resume the game | Turn | S
15 | Produce sound for throw of a dice / moving pawn / win screen / special actions | Turn | C
16 | Display dice throw / moving pawn with an animation | Turn | C
17 | Menu extended with "settings" button (for example, containing screen resolution, audio volume, …) | Menu | C
18 | Possibility to select also computer players | Init | C
19 | Computer player is able to play the game | Turn | C
20 | Add some humour to the computer player | Turn | W
21 | Save current state of the game on a file | Turn | C
22 | Load a previously saved game state | Menu | C
23 | Make game playable online | Browser | C
24 | Make game playable by users sitting at different PCs (LAN multiplayer) | Menu and Turn | C
25 | Instructions show on first start up | Menu | C

## SPRINT 1 BACKLOG
SPRINT 1 BACKLOG
ID | User story | Priority | Time Estimation | Tasks | Acceptance criteria
EXAMPLE
ID | User story | Priority | Time Estimation | Tasks | Acceptance criteria
1 | As a player I want to start the game from the menu, so that I can play it. | M | [1] | - Find a proper button texture - Load and display button texture on run - When clicked on screen, retrieve position - If clicked on start button, init game | - Button displayed on menu screen - Button has a reasonable size compared to screen dimension - Clicks not on the button area have no effect on game start - Clicks on the button area make the screen change (to init phase)
1 | As a player I want to quit the program from the menu, so that I can stop playing. | M | [1] | - Find a proper button texture - Load and display button texture on run - When clicked on screen, retrieve position - If clicked on exit button, quit program | - Button displayed on menu screen - Button has a reasonable size compared to screen dimension - Clicks not on the button area have no effect on quit program - Clicks on the button area make the program quit