## PRODUCT BACKLOG
PRODUCT BACKLOG
ID | Feature | Category | Priority | Sprint 1 | Done? | Sprint 2 | Done | Sprint 3 | Done
0 | Display menu screen on program start | Menu | M | x | Ja
1 | Menu with "start game" and "exit" buttons | Menu | M | x | Ja
2 | Show the rules of the game when needed by user | Menu or Turn | M |  |  | x
3 | Screen to name players | Menu | C
4 | Display game board | Init | M |  |  | x
5 | Place the boats on the starting positions | Init | M
6 | Display "exit" button | Init and Turn | M |  |  | x
7 | Display which player is playing the current turn | Turn | M
9 | Let the player move their boats in the amount of steps they are allowed to take | Turn | M
10 | Execute special actions when cards are activated | Turn | M
11 | Change current player after the end of the turn | Turn | M
12 | Show win screen if all enemy boats are destroyed | End | M
13 | "Go back to menu" button is displayed in the win screen | End | S
14 | Current player can pause and resume the game | Turn | S
15 | Produce sound for Moving boats, winning, special moves | Turn | C
16 | Display animation for moving boats | Turn | C
17 | Menu extended with "settings" button | Menu | C |  |  | x
18 | Possibility to select also computer players | Init | C
19 | Computer player is able to play the game | Turn | C
20 | Add some humour to the computer player | Turn | W
21 | Save current state of the game on a file | Turn | C
22 | Load a previously saved game state | Menu | C
23 | Make game playable online | Browser | C
24 | Make game playable by users sitting at different PCs (LAN multiplayer) | Menu and Turn | C
25 | Instructions show on first start up | Menu | C
26 | Create a github folder | None | M | x | Ja
27 | Create a card list | None | M |  |  | x
28 | Create Highscore | Menu | S |  |  | x

## SPRINT 1 BACKLOG
SPRINT 1 BACKLOG
ID | User story | Priority | Time Estimation | Tasks | Acceptance criteria
0 | As an user I want to see a menu when I start the game, so I can start a new game or exit the game | M | 12 | - Create a "Start game" button - Create a "Exit" button | - The exit Button works - Start button shows
1 | As an user I want a menu with buttons, so I can start and exit the game | M | 5 | - Create 2 buttons - Place buttons on right position | - 2 Buttons - The buttons on the right positions
26 | Create a github folder | M | 1 | - Create a folder structure - Give everybody rights to push & pull | - A proper folder structure - Everybody in our group has excess to the git

## SPRINT 2 BACKLOG
SPRINT 2 BACKLOG
ID | User story | Priority | Time Estimation | Tasks | Acceptance criteria
2 | As an user I want to be able to look at the rules at any time, so I know what I'm supposed to do | M | 8 | - make a tab with all the rules - Make a button in menu named "Rules" | - The rulebook is shown - The rulebook is readeble for the user - users can access the rules in game and in the menu
4 | As an user I want a playing field, so I am able to play the game | M | 40 | - Design a playing field - Implement playing field in code | - A proper playing field - playing field is shown when pressing "start game" - Playing field goes away when pressing "Exit button"
6 | As an user I want to be able to quit the game at any time when I am playing the game, so I can go do something else | M | 5 | - Place the Quit button on the playing field - let the Quit button go back to the menu | - Quit button goes to the menu - Quit button is visible for the user
17 | As an User I want a settings tab, so I can turn off the music | C | 8 | - Create a settings button in the menu - Create an option to shut down music - Create a "Back" button to go back to the menu | - Settings button in Menu - Option to turn on/off music
27 | As an user I want to have a card deck, so I can use cards in my turn when I am playing the game | M | 20 | - Create a card list in a database or list - Give a value to the cards | - Cardlist in the database
28 | As an user I want to see the best scores, So I can know what I have to beat | S | 13 | - Create a database - Create database connection - Get a list with Highscores | - A list of highscores